GREENOPS VERIFY  |  TEAM BRIEF

TEAM BRIEF / 01

# One product. Two tested ways to reduce waste.

Keep GreenOps at the centre: audit cloud resources, forecast demand, compare cost and carbon, then approve and verify a bounded change.

Working title: GreenOps Verify. Add only one SpendProof-inspired feature: an AI Efficiency Lab that checks whether a support workflow can use fewer unnecessary calls or less irrelevant context without losing required behaviour. It shares the same evidence, approval and verification flow; it is not a separate subscription product.

## The user and the promise

User: an engineering lead running an AI-enabled support service on GCP. Their question: “Which changes should we make this week to reduce waste while preserving our workload and support-policy requirements?” The output is an evidence-backed change proposal, trial results, a scoped approval and a verified result—not just advice.

| Retain from GreenOps | Build as the new contribution |
| --- | --- |
| Cloud audit and recommendations | Cross-source evidence through Zetaris, with stable IDs and timestamps. |
| Forecasts and impact comparisons | Target-capacity checks, repeatable workload trials, explicit cost/carbon assumptions. |
| Execution and reporting | Approval enforced in code, fresh-state checks, read-back and recovery status. |
| Agent coordination | A critic sends failed plans back for revision; Meterless preserves tested outcomes. |
| Environmental purpose | Keep carbon estimates visible and scoped. Never convert AI token counts directly into CO2e. |

## The demonstration in plain English

A worker looks idle on average. The agent proposes shrinking it, but the critic finds a peak workload that will not fit and rejects that plan. The agent investigates a different cloud candidate. In the AI lab, aggressive context trimming misses a premium-return rule, so it too is rejected. A revised candidate is tested, approved in the sandbox and verified. After restart, Meterless recalls the rejected experiment; a new policy version triggers reevaluation.

No guaranteed savings, no zero-downtime claim, no fake sponsor integration. “No acceptable change found” is a valid outcome when the tests do not pass.

TEAM BRIEF / 02

# Keep the stack small and the sponsors essential

| Component | Build decision |
| --- | --- |
| Python + Google ADK | Retain the base approach. Four meaningful roles: coordinator, investigator, optimizer and critic. |
| Streamlit + FastAPI | One interface with review queue, candidate comparison, evidence drawer and approve/verify controls. |
| Zetaris — required | Read-only investigation across BigQuery cloud records, PostgreSQL AI outcomes and a supported file source. At least two physical sources must actually work. |
| Meterless — required | TypeScript H-MEM reference behind a private sidecar. Persist rejected trials, verified corrections and their provenance. Action authority stays in PostgreSQL. |
| Cursor + NVIDIA | Use Cursor during development. Test a NVIDIA-hosted model through a supported adapter; pin the working dependency set. |

The guide requires Zetaris, Meterless and Cursor, with NVIDIA wherever it contributes. H-MEM is a reference implementation/specification, not a billing or rollback service. Follow the supplied sponsor resources; do not invent vendor SDK calls. [H1 §8; M1–M2; Z1–Z3]

TEAM BRIEF / 03

# Six days: build the proof before the polish

Planning assumption: three builders with web/API experience. For two builders, remove the second model, automatic slides and live cloud resize first.

| Date / owner | Deliverable that must work |
| --- | --- |
| 22 Oct ¦ Integration + agent leads | Real Zetaris query; real Meterless memory survives restart; one model/tool call; a basic investigation. |
| 23 Oct ¦ Agent + trial leads | Cloud candidate, deterministic capacity/impact checks and a critic-driven revision or justified rejection. |
| 24 Oct ¦ Trial + integration leads | One AI workflow with actual traces, independent checks and development/held-out separation. |
| 25 Oct ¦ API + test leads | Human approval bound to plan/version; sandbox execution and read-back; stale and duplicate-action tests. |
| 26 Oct ¦ Whole team | Feature freeze; acceptance suite; clean-install test; deck and 1–4 minute video prepared. |
| 27 Oct ¦ Submission owner | Final links, provenance, credentials and limitations checked. Internal target 18:00 UTC; official guide deadline 23:45 UTC. |

## Day-one go/no-go gate

Do not spend two days polishing a disconnected frontend. First establish sponsor workspace access, connector reachability, model/tool compatibility and a persistent memory service. A remote Zetaris workspace cannot automatically reach a laptop database. Use an approved reachable sample source or request support immediately.

## Minimum scope

GCP only; six small VM histories; one service; up to three candidate plans per path (six total); one sandbox action; one AI workflow. Prefer an owned disposable GCP trial when permissions, spend controls and compatibility are confirmed. Otherwise execute a real local worker/configuration change, clearly labelled as a local analogue—not a GCP resize.

## Two questions to resolve before code reuse

No licence grant was found in the inspected GreenOps tree or README. Obtain permission covering reuse and redistribution before copying code or assets; attribution alone is not permission. Ask organizers whether a derivative of another team’s previously winning project is eligible and whether it belongs in Wildcard. Until clarified, independently implement the concept and plan for Track 02. [R1; L1; H1 §§4, 9]

The supplied guides and public page disagree on registration time and judging start. Use the earlier registration cutoff (22 Oct, 23:45 UTC), be demo-ready on 26 Oct, and confirm the controlling schedule on HackOS. Submission agrees: 27 Oct, 23:45 UTC / 28 Oct, 05:15 IST. [H1; E1]

TEAM BRIEF / 04

# What the judges should see

| Time | Show this, not a promise |
| --- | --- |
| 0:00–0:25 | The problem: a cheaper change can break a cloud service or an AI answer. Identify the selected service and workload requirements. |
| 0:25–0:55 | A real Zetaris-backed query and evidence receipt from separate sources. |
| 0:55–1:35 | A rejected cloud candidate with its peak-capacity evidence, followed by a revised trial. |
| 1:35–2:10 | The AI lab catches a missing policy exception and retests a revised configuration. |
| 2:10–2:55 | Human approval, fresh-state check, scoped sandbox action and read-back/health verification. |
| 2:55–3:30 | Restart and recall through Meterless; a changed policy makes old validation inapplicable. |
| 3:30–3:55 | Actual test results, estimated carbon coverage, limitations and what was newly built. |

## The submission package

Provide the working repository and clean setup instructions, a 1–4 minute video, slide deck and an explanation of Zetaris, Meterless, Cursor and NVIDIA use. Declare original inspiration, permitted reused components, pre-event plans/data and the code built during the eligible window. The guide’s rubric is Impact 30, Technical 20, Innovation 15, Demo 15, Product/UX 10 and Sponsor Tech 10. [H1 §§9, 12]

## Evidence to publish

Publish candidate decisions and failures, required-check results by case type, measured trial cost, cost per accepted task, latency, source freshness, memory-recall behaviour, stale-approval blocks and duplicate-action handling. Separate measured observations, projected costs and carbon estimates. A small synthetic evaluation does not prove production reliability.

## Read the detailed companion documents

The 28-page Complete Blueprint explains the design and cites 28 sources/materials. The Developer Handoff contains module contracts, the implementation backlog, test cases and Cursor instructions. This Team Brief is an alignment document, not a claim that the product is already built.

## Key source links

[LINK] Event page

[LINK] Original GreenOps repository

[LINK] Meterless H-MEM reference

[LINK] Zetaris connector documentation